## Slide 1
AI Development Pilot
Lessons Learned & Path Forward
March 2026 | Prepared by Chris Hoffman, Chief Architect
Notes: Welcome. This presentation covers the findings from our first AI-assisted development pilot, which ran March 17-20 with a single pod team. I'll walk through what we learned, what we need to fix, and our path forward.

## Slide 2
Executive Summary
3 Key Findings
1. Infrastructure automation gaps consumed an estimated 50%+ of pilot time
2. AI agents produced quality output when given proper architectural context
3. Systematic deployment issues affect ALL development — not just AI-assisted work
3 Critical Actions
1. Template automation pipeline — 10-minute deployment target
2. Standardized pre-pod checklist — 1 week in advance
3. Mandatory team kickoff — Engineering, Architecture, Product & QA in the same room
Recommendation: Pause new pods until these 3 actions are complete. Resume with confidence.
Notes: Three findings, three actions. The headline is clear: infrastructure gaps, not AI limitations, are the bottleneck. AI is an engineer multiplier — it amplifies productivity when given proper context. The troubleshooting and context-gathering demands of this process require more skilled engineers, not fewer.

## Slide 3
Pilot Overview
4-Day AI-Assisted Development Pilot | March 17–20, 2026
Pod Team
Engineer: Krista
Product Owner: Lauren
QA: Nelly
Team Support
Architecture: Tim Medina
Infrastructure & CI/CD: Kyle Maggard
Project Scope
New microservice development
AI-assisted coding with Claude Code + SpecKit
Executive Sponsor: Chris Hoffman
Notes: This was our first pod. A single engineer, Krista, supported by Lauren as product owner and Nelly for QA. Tim provided architecture support and Kyle handled infrastructure. The project was building a new microservice using AI-assisted development tools.

## Slide 4
Where Did the Time Go?
50%+
Infrastructure & Setup
~50%
Actual Development
Top 5 Blockers — Ranked by Time Impact
1. Tooling Setup & Configuration
MCP servers, Docker Desktop, DBeaver — none pre-configured
2. IT Ticket Overhead
~5-6 formal tickets + ~30 unlocks = 35 access requests for one engineer
3. Environment Configuration
DB connectivity crisis — multiple repos creating secrets with no coordination
4. CI/CD Pipeline Issues
Jenkins-to-CircleCI migration confusion, legacy files, 10-min deploy cycles
5. Routing & Deployment Failures
K8s pods green but endpoints unreachable — recurring pattern
Notes: The team estimated more than half their time was consumed by infrastructure rather than building features. Five categories of blockers, ranked by time impact. The most significant: basic tooling wasn't set up before day 1, and we submitted roughly 35 tickets or access requests just to get a working environment. These are problems that affect all development, not just AI-assisted work.

## Slide 5
What Went Well
✓
AI output quality with proper context — When given existing table structures and event formats, agents produced functional schemas with proper patterns
✓
Product owner engagement — Lauren: "Oh wow, this is really cool"
✓
Executive validation — Bobby asked Krista if she'd go back to the old process. She said: "No way — I want to continue using this"
✓
Team collaboration — Strong cross-functional engagement once technical barriers resolved
✓
Infrastructure automation vision — Kyle worked until 2am on pipeline improvements — team commitment to solving this permanently
✓
AI as engineer multiplier — Skilled engineers essential for context, architecture, and validation; AI multiplies their output
Notes: Despite the infrastructure challenges, there were clear wins. The strongest signal: when AI agents received proper context, the output quality was excellent. Both Lauren and Krista had strongly positive reactions. Bobby's direct question to Krista and her emphatic response tells us the engineers want to keep going. And Kyle's commitment — working until 2am to fix the pipeline — shows this team is invested in making this work.

## Slide 6
Major Blockers — Ranked by Impact
1
Tooling Setup & Configuration
CRITICAL
MCP servers not configured. Docker Desktop missing. DBeaver blocked by security whitelist.
2
IT Ticket Overhead
HIGH
~5-6 formal tickets + ~30 unlocks needed. Each post-facto request = process failure.
3
Environment Configuration
HIGH
DB connectivity crisis: repos independently created secrets/users with no coordination.
4
CI/CD Pipeline Issues
MEDIUM
Jenkins-to-CircleCI confusion. Legacy Jenkins files confused AI agents. 10-min deploy cycles.
5
Routing & Deployment Failures
MEDIUM
K8s pods green but endpoints unreachable. Recurring pattern: "We always have these routing issues."
Notes: These five categories consumed the majority of the team's productive time. Notice these are all infrastructure problems, not AI problems. The tooling should have been set up before day 1. The ticket overhead was staggering — roughly 35 access requests for one engineer to do basic development work. The database connectivity crisis happened because two repos independently created their own secrets with no coordination. And the Jenkins-to-CircleCI migration left legacy files that actively confused the AI agents.

## Slide 7
Root Cause: Infrastructure, Not AI
The AI agents worked well. The infrastructure around them didn't.
✓ With Context
Tim provided existing table structures, DDL, and event formats upfront
Result: Functional schemas with proper outbox patterns, immediately correct — zero rework required.
✗ Without Context
DB structures from 2 existing apps not provided. MSK topics and event schemas missing.
Result: Wrong field sizes (50-char vs 70-90 needed), missed existing tables, full rework cascade.
These challenges affect ALL development teams. The pilot surfaced problems that have always existed but were absorbed by expert intervention.
Notes: This is the key insight. The AI agents performed well when given proper context. When context was missing, they made reasonable assumptions that turned out to be wrong. This isn't an AI problem — it's a preparation and infrastructure problem. And critically, these same issues slow down all of our development teams. The pilot just made them impossible to ignore.

## Slide 8
Action 1: Template Automation Pipeline
BEFORE
4+ days to get a running environment
Required expert Kyle intervention
Multiple manual configuration steps
No validation of successful deployment
→
AFTER — 10-Minute Target
Clone repo, run script — live in 10 minutes
Interactive deployment: K8s, EKS, or ECS
Auto-configured: health monitoring, Datadog, CI/CD
Hello World validation: UI, API, and DB
Teardown capability for dev environments
Owner: Kyle Maggard | Status: In Progress | Deadline: Before next pod launch
Why: Eliminates the pipeline variable. If the next pod hits challenges, we can confidently attribute them to AI performance — not infrastructure.
Notes: This is our highest-impact action. Today it takes 4+ days and expert intervention to get a running environment. The target: 10 minutes, self-service, zero expert dependency. Kyle is already working on this. The deployment script will walk through required parameters, auto-configure everything, and validate that the full stack is working — UI, API, and database. Kyle has the authority to eliminate tech debt without approval delays to get this done.

## Slide 9
Action 2: Pre-Pod Setup Checklist
1-Week Advance Verification
All tooling verified (MCP servers, Docker, VS Code, DB tools)
Repository access confirmed — no 404s on day 1
Environment credentials and secrets provisioned
CI/CD pipeline tested with hello world deployment
Database connectivity validated end-to-end
Reference Materials Package
Architecture diagrams
As-is and to-be state
Integration surface documentation
Every upstream and downstream touchpoint
Existing table DDL & CDC event structures
Complete snapshots, no assumptions
API contracts
OpenAPI specs from upstream services
Network topology & deployment patterns
K8s, routing, environment configs
Owner: Tim Medina (reference materials) + Kyle Maggard (infrastructure verification) | Deadline: 1 week before pod launch
Notes: The checklist is simple but critical. Every participant must have verified tooling, access, and a working environment one full week before the pod starts. No exceptions. The reference materials package ensures we have all the architectural context documented and ready for the AI agents from the moment we engage them. Tim owns the reference materials and architecture context. Kyle owns infrastructure verification.

## Slide 10
Action 3: Team Design Kickoff
Engineering + Architecture + Product + QA — Same Room
1
Review As-Is
Architecture in context of
Experity platform
→
2
Whiteboard Feature
Map every system interaction
end-to-end
→
3
Document ALL Touchpoints
Table names, schemas, CDC events,
field sizes, API contracts
→
4
Populate & Engage
Fill integration surface folder
then engage AI agents
Non-negotiable: AI agents are NOT engaged until the integration surface folder is complete and validated.
Integration Surface Folder Contents: Touchpoints outside scope of work
db-schemas/
DDL snapshots from external databases
events/
MSK/Kafka event structure definitions
api-contracts/
OpenAPI specs from upstream APIs
Notes: This is the most important action for AI output quality. Everyone needs to be in the same room — engineering, architecture, product, and QA. We whiteboard the feature, map every system interaction, and document every upstream and downstream touchpoint. AI agents are not engaged until this folder is complete and validated. The pilot proved this beyond doubt — when Tim gave agents this context upfront, they produced correct code immediately. When it was missing, we got cascading rework.

## Slide 11
Next Pod Success Plan
Pre-Pod Prerequisites (1 week before)
Template automation deployed and tested (10-min target)
Setup checklist distributed and verified by all participants
Integration surface documents prepared and validated
Repository access and credentials confirmed
CI/CD pipeline validated with hello world
Day-1 Protocol
Architecture review & whiteboard (full team, same room)
Integration surface documentation populated
Workspace structure set up
THEN engage AI agents
Success Metrics
Metric
Pod 1 (Actual)
Next Pod Target
Environment setup
4+ days
< 10 minutes
Day-1 ticket blockers
10-11tickets
+ ~30 unblocks
Zero
Dev vs. infra time
~50%
80%+
AI rework from context gaps
Full schema rebuild
Near zero
Notes: Here's the concrete plan. One week before: everything automated, verified, and distributed. Day 1: architecture review, whiteboard session, populate integration context — and only then engage the AI agents. The metrics table shows what we're targeting. If we hit these numbers, we'll know the infrastructure improvements worked. And if the next pod encounters challenges, we'll know they're genuine AI or process issues worth investigating — not the same infrastructure problems we've already identified.

## Slide 12
Recommendation
1. Pause new pods until the 3 critical actions are complete.
2. Continue the AI pilot with confidence — infrastructure, not AI, was the bottleneck.
3. AI is an engineer multiplier. These fixes benefit ALL development.
Questions & Discussion
Notes: To close: we recommend pausing new pods until template automation is complete, the setup checklist is verified, and the team kickoff protocol is established. Once those are in place, we resume with confidence. The pilot proved the concept works — AI-assisted development delivers real value when the infrastructure supports it. And critically, fixing these infrastructure gaps benefits every development team, not just AI-assisted pods. This was an infrastructure discovery as much as an AI pilot. I'm happy to take questions.